## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anirudh | 2024-11-15 | GPU non-availability for YOLO Model Training | S2 | Anirudh | Logical | Used Google collab to trained the Yolo Model | 2024-11-17 | Closed | Completed
2 | Anirudh | 2024-11-23 | Sort module not having class ID | S3 | Anirudh | Logical | Used the YOLO Model | 2024-11-28 | Closed | Completed
3 | Anirudh | 2024-12-30 | Vehicle classification | S3 | Anirudh | Logical | Get the vehicle id and pass for classification. | 2024-12-05 | Closed | Completed
4 | Anirudh | 2024-12-20 | Missing detection in some frame | S4 | Anirudh | User Interface | Created the bounding boxes | 2024-12-26 | Closed | Completed
5 | Anirudh | 2024-12-26 | Data Interpolation | S4 | Anirudh | Maintainability | Create a Result score and determined on the score | 2024-12-29 | Closed | Completed